## Slide 1: Structuring work for flow and value through collaborative planning
Gregory Howell
Lean Construction Institute

## Slide 2
What is an Owner buying?
What is the nature of Projects?
What is the work in projects?
What sort of organization is appropriate?

## Slide 3: What are Owners Buying?
An Owner must decide what they are buying: A completely defined product or the services of a team trying to solve a problem that no one completely understands and keeps changing.
Jim Carroll, 1989

## Slide 4: What is the nature of projects
Simple
&
Certain
Complex
& Uncertain

## Slide 5
Uncertain about what & how
Certain about What
Certain about what and how
Certain about How
What to Build
How to Build
Reducing Uncertainty: The work in projects

## Slide 6
1
10
5
5
10
1
Traditional Procurement
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 7
✪
1
10
5
5
10
1
Ends & Means Uncertainty
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 8
1
10
5
5
10
1
Uncertainty on Typical Projects at Start of Construction 1990
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 9
1
10
5
5
10
1
Uncertainty at Start of Construction on Most Recent Project - 1990
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 10
1
5
10
Uncertainty on Typical Building Projects At Start of Construction - 2011
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 11
Uncertainty at Start of Construction on Typical
High Tech Projects - 2011
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 12
Ends & Means Uncertainty at Start of Construction on Most Recent Building Project 2011
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 13
Uncertainty on Most Recent Project
High Tech - 2011
Certain Objectives
Uncertain Means
Uncertain Objectives
Uncertain Means
Certain Objectives
Certain Means
Uncertain Objectives
Certain Means
Uncertainty about What to build
Uncertainty about How to Build

## Slide 14
Independent
Winning – Statistical improbability
Planning – player selection
Coaching – Skills and situation response
Interdependent
Win - Ability to work together
Coaching - Communication, conversation and listening skills
American Football
Sequentially dependent
Win by making & following plan and …
Coaching in skill and individual response
Game Plans – Robert Keidel
Baseball
American Football
Soccer
Basketball

## Slide 15
Uncertain about what & how
Certain about What
Certain about what and how
Certain about How
What to Build
How to Build
Reducing Uncertainty: The work in projects

## Slide 16: Managing in Uncertainty
Commanders intent – Focus on Purpose
Power to the Edge - Local Initiative
Willingness to share pains and gains: Honor
Rapid learning – What works where
Horizontal communication
Relationship of Senior to Junior: Scholar to Student
http://vimeo.com/45947817